## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Import physical document | Staff | Medium | Iteration 1
Borrow physical document | Employee,Staff | Simple
Retrieve borrowed document | Staff | Medium
Search physical document | Employee, Admin | Simple | Iteration 1
Upload digital document | Employee, Admin | Simple
Delete digital document | Employee, Admin | Simple
Edit digital document | Employee, Admin | Simple
Search digital document | Employee, Admin | Simple
View digital document | Employee | Simple
Authentication | Staff, Employee, Admin | Simple | Iteration 1
Create user | Admin | Medium | Iteration 1
Search users | Admin | Medium | Iteration 1
Disable user | Admin | Simple | Iteration 1
Check capacity of physical room/locker/folder | Admin, Staff | Simple
Export physical document | Staff | Simple
Create user group | Admin | Simple
Add user to user group | Admin | Simple
Asign role to user | Admin | Simple
Delete user group | Admin | Simple
Add room | Admin | Simple | Iteration 1
Add locker | Staff | Simple | Iteration 1
Add folder | Staff | Simple | Iteration 1
Remove room | Admin | Simple | Iteration 1
Remove locker | Staff | Simple | Iteration 1
Remove folder | Staff | Simple | Iteration 1
Create section | Admin | Simple
Create digital folder | Admin | Simple
Remove section | Admin | Simple
Remove digital folder | Admin | Simple
View audit log | Admin | Simple
Edit physical document metadata | Admin | Simple
Move physical document | Staff | Simple
Auhorization physical document | Admin | Complex | Iteration 1
Authorization digital document | Admin | Complex