## Product Backlog
Document Management System
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | Back-end | Front-end | Actual Code Iteration
Import physical document | Staff | Medium | Iteration 1 | ChienNQ | KhanhNG
Borrow physical document | Employee,Staff | Simple
Retrieve borrowed document | Staff | Medium
Search physical document | Employee, Admin | Simple | Iteration 1 | KhoaVD | KhanhNG
Upload digital document | Employee, Admin | Simple
Delete digital document | Employee, Admin | Simple
Edit digital document | Employee, Admin | Simple
Search digital document | Employee, Admin | Simple
View digital document | Employee | Simple
Authentication | Staff, Employee, Admin | Simple | Iteration 1 | ChienNQ | KhanhNG
Create user | Admin | Medium | Iteration 1 | KhoaVD | KhanhNG
Search users | Admin | Simple | Iteration 1 | BaoNHD | KhanhNG
Disable user | Admin | Simple | Iteration 1 | CuongLT | KhanhNG
Check capacity of physical room/locker/folder | Admin, Staff | Simple
Export physical document | Staff | Simple
Create user group | Admin | Simple
Add user to user group | Admin | Simple
Asign role to user | Admin | Simple
Delete user group | Admin | Simple
Add room | Admin | Simple | Iteration 1 | KhoaVD | KhanhNG
Add locker | Staff | Simple | Iteration 1 | BaoNHD | KhanhNG
Add folder | Staff | Simple | Iteration 1 | CuongLT | KhanhNG
Remove room | Admin | Simple | Iteration 1 | KhoaVD | KhanhNG
Remove locker | Staff | Simple | Iteration 1 | BaoNHD | KhanhNG
Remove folder | Staff | Simple | Iteration 1 | CuongLT | KhanhNG
Create section | Admin | Simple
Create digital folder | Admin | Simple
Remove section | Admin | Simple
Remove digital folder | Admin | Simple
View audit log | Admin | Simple
Edit physical document metadata | Admin | Simple
Move physical document | Staff | Simple
Auhorization physical document | Admin | Complex | Iteration 1 | ChienNQ | KhanhNG
Authorization digital document | Admin | Complex